## Sprint Task Board
Sprint #2 Task Board/Chart
Each Feature | Points | Tasks [hours] | Tasks [hours] | Tasks [hours] | Tasks [hours] | Tasks [hours] | Sum of Effort-Hour Estimate
User Registration | 1 | Create user table [2] | Format page [3] | Create input fields [3] | Watching tutorials [2] | Database setup [1] | 11
User Login | 1 | Create page layout [3] | Query the database [2] | Prompt to sign up [2] | Watching tutorials [2] | Assign correct user type [3] | 12
Individual Profiles | 1 | Create page layout [3] | Allow input fields [2] | Save info [2] | Watching tutorials [2] |  | 9
Team Profiles | 2 | Create page layout [3] | Link teammates [4] | Add logo [5] | Watching tutorials [5] | Allow input fields & save [4] | 21
Project Details | 1 | Create page layout [3] | Allow input fields [2] | Drop down details [3] | Watching tutorials [2] |  | 10
Project Bidding | 2 | Create page layout [3] | Allow team leader only [4] | Drop down rankings [4] | Submission [2] | Watching tutorials [5] | 18
Total effort hours
Total Story Points | 8 | [5 empty] | 81

## Group Burndown chart
Initial: Total Hours Estimated | 150
Number of Days in Sprint | 16
How to reference data from another sheet | "=Sheet1!A1"
Days | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Note
Actual Hours | 7.6 | 16.5 | 18.5 | 16.4 | 4.5 | 1.5 | These numbers come from the Sprint Task Board
TA wont notice this \/
we are the best group

## Ivens
User Story | Tasks | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6
As a consumer, I would like to use a simple page to login and access my personal account | #REF! | 0.2 | 0.5 | 0.2 | 0.1 | 1
| #REF! | 0.3 | 0 | 0.5 | 0.2
| #REF! | 0.1 | 0 | 0.3 | 0.1
Subtotal | Overall | 0.6 | 0.5 | 1 | 0.4 | 1
Note: This column references Estimates from the Sprint Task Board. Do not edit on this page.
Individual Burndown Chart

## Michelle
User Story | Tasks | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6
As the client, I would like a page that will display products I will market towards my retail customers. | #REF! | 0 | 1 | 0 | 0
| #REF! | 0 | 2 | 2 | 1
| #REF! | 2 | 2 | 1 | 1
Subtotal | Overall | 2 | 5 | 3 | 2
As the client, I would like a page that will display my products to my commercial clients (educators). | Create page layout [3]
Allow team leader only [4]
Drop down rankings [4]
Individual Burndown Chart

## John
User Story | Tasks | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6
As a client, I would like a Twitter feed integrated with the announcements | #REF! | 0 | 1 | 0 | 1 | 0 | 1
| #REF! | 0 | 2 | 2 | 0 |  | 0
| #REF! | 0 | 0 | 1 | 2 | 3 | 0
Subtotal | Overall | 0 | 3 | 3 | 3 | 0 | 0
Individual Burndown Chart

## Damian
User Story | Tasks | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6
As the seller, I would like to be able to sell my products at different prices depending on the type of user that is looking to purchase. | Create page layout [3] | 1 | 0 | 0 | 0
| Allow input fields [2] | 0 | 3 | 4 | 1
| Save info [2] | 0 | 0 | 2 | 2
| Watching tutorials [2] | 0 | 0 | 0 | 3
Subtotal | Overall | 1 | 3 | 6 | 6 | 0
Note: This column references Estimates from the Sprint Task Board. Do not edit on this page.
Individual Burndown Chart

## Mark
User Story | Tasks | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6
As a customer, I would like to be able to add things to my cart | Create page layout [3] | 2 | 0 | 0 | 0 | 0 | 0
| Allow input fields [2] | 0 | 2 | 0 | 0 | 0 | 0
| Drop down details [3] | 0 | 0 | 2 | 1 | 1 | 0
| Watching tutorials [2] | 0 | 0 | 0 | 2 | 1 | 1
Subtotal | Overall | 2 | 2 | 2 | 3 | 2 | 1
Individual Burndown Chart

## Raul
User Story | Tasks | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6
As a developer, I would like to have product information integrated in a database. As a client, I would like to be able to add, edit and delete products | server routes, models, controllers, tutorials [4.5] | 2 | 2 | 0.5 | 0 | 0 | 0
| Format page [3] | 0 | 1 | 1.5 | 0 | 0 | 0
| Create input fields [3] | 0 | 0 | 1.5 | 0.5 | 0 | 0
| Create Product view and controller functions [3] | 0 | 0 | 0 | 1.5 | 1.5 | 0
| Products edit view and routing (non functional) [0.5] | 0 | 0 | 0 | 0 | 0 | 0.5
Subtotal | Overall [12.5] | 2 | 3 | 3.5 | 2 | 1.5 | 0.5
Individual Burndown Chart